## Testcases
Sr. No | Test Case ID | Product | Scenario id | Test Scenario | Test Cases | Expected Result | Actual Result | Remark & Details | Screenshots | Vehicle Registration No. (used) | Policy Number
1 | TC_01 | Motor | SC_01 | STP Flow Policy Issuance Journey | 1. New Business (New Car) Inclusive of Addons | End to end journey | Pass | [tf-api FG] New Business (F13) Comprehensive incl. add-on combo ZDCNE ISSUED end-to-end TODAY. Honda City (1.5 petrol), PAN DHQPG4064J. IDV ₹8,35,142, gross ₹36,894. | 1 | KA03MZ2682 | 132/14/11/0729/MTP/2410003355
2 | TC_02 | Motor | SC_01 | STP Flow Policy Issuance Journey | 2. Standalone OD Inclusive of Addons | End to end journey | Pass (bind pending FG) | [tf-api FG] Standalone OD + add-ons: live FG quote verified with THIS vehicle — Kia Seltos D1.5, SAOD gross ₹20,721 (IDV ₹5,62,360). Journey already proven end-to-end on 29-Jul (SAOD policy 132/18/11/0827/MOD/2410003312 bound during the rollover-working window). Fresh binding is currently blocked FG-side (rollover CreateProposal returns 'Vehicle Age is not Configured for this Rule' — GCI's rollover rule deployment in progress, confirmed by GCI mail). | 2 | CG04ND5888 | Pending (FG rule fix)
3 | TC_03 | Motor | SC_01 | STP Flow Policy Issuance Journey | 3. Comprehensive- Inclusive of Add ons | End to end journey | Pass (bind pending FG) | [tf-api FG] Rollover Comprehensive + add-ons (ZDCNE): live FG quote verified with THIS vehicle — Hyundai Aura 1.2, gross ₹19,989 (IDV ₹3,48,480). Journey proven end-to-end 29-Jul (policy 132/02/11/0827/MTP/2410003313). Fresh binding is currently blocked FG-side (rollover CreateProposal returns 'Vehicle Age is not Configured for this Rule' — GCI's rollover rule deployment in progress, confirmed by GCI mail). | 3 | TS16EZ2345 | Pending (FG rule fix)
4 | TC_04 | Motor | SC_01 | STP Flow Policy Issuance Journey | 4. Third Party - Inclusive of Additional covers | End to end journey | Blocked (FG UW) | [tf-api FG] TP request is well-formed (AgentCode fix d460843; TP prices on some vehicles) but GCI confirmed standalone TP is BLOCKED for this channel per UW guidelines — every vehicle declines ("Referral due to: Declined Vehicle"). FG hidden on TP compares. | 4 | RJ14YC4219 | N/A
5 | TC_05 | Motor | SC_01 | ELECTRIC Car - Comprehensive | Policy Issuance Journey - BATTERY OPERATED | End to end journey | Pass | [tf-api FG] Electric car (BATTERY OPERATED) Comprehensive ISSUED new-business. MG ZS EV (ZS EV), PAN DHQPG4064J. IDV ₹19,94,810, gross ₹57,060. (Nexon EV now on FG's revised decline list — decline list churned 26-28 Jul.) | 5 | GJ01WK2700 | 132/14/11/0729/MTP/2410003322
6 | TC_06 | Motor | SC_02 | CPA Cover - Exclusion - New Business | Rollover - PA cover for Owner driver Exclusion Tab - 1) I do not have a valid driving license to drive the above vehicle. Yes / No. 2 ) Do You have valid PA Cover Policy for SI 15 Lakhs and Above (Including Death , Total disability, partial disability) - YES / No. (Previous PA policy Name / Policy No / Sum insured / Expiry date) | If 'Yes" go ahead to policy issuance. If "No" Need to take CPA cover. | Info | [tf-api FG] CPA owner-driver exclusion (valid DL / existing PA >=15L): portal-level declaration; API prices CPA at proposal (CPAReq=N at quote, CPA block with nominee at CRT). | 6 | N/A | N/A
7 | TC_07 | Motor | SC_03 | Insured Declared Value - Increase & Decrease For New Business | IDV Validation :- STD IDV + 20% & -20% | IDV should not allowed beyond our guidelines (Min IDV/ STD Idv / Max Idv) | Pass | [tf-api FG] IDV +/-20% guardrail: VW Polo GT quotes at STD IDV ₹2,91,000 (gross ₹5,907); within-band IDVs reprice, beyond +/-20% FG referral-declines with 'IDV Variation'. Portal shows min/STD/max IDV slider. | 7 | KA01MX9122 | N/A
8 | TC_08 | Motor | SC_04 | Elec. Accessories & Non electrical accessories IDV - Comprehensive | Was Elec Accessories on opted in the customer's previous policy | If 'Yes" go Ahed to policy issuance if eligible . If "No" provide the inspection or go Ahed with without Add on. | Info | [tf-api FG] Electrical accessories IDV: accessoriesSumInsured is an ICICI-only canonical field; FG provider does not send it. Portal gates on previous-policy fitment. | 8 | N/A | N/A
9 | TC_09 | Motor | SC_05 | LPG /CNG Kit - Comprehensive | Was External fitted on opted in the customer's previous policy | If 'Yes" go Ahed to policy issuance if eligible . If "No" then system should not be allowed to proceed further. | Info | [tf-api FG] External CNG/LPG kit: bifuel-kit SI is ICICI-only; FG payload carries CNGOrLPG.InbuiltKit only. Portal gates the previous-policy question. (Real CNG plate available: MH43AT4924.) | 9 | MH43AT4924 | N/A
10 | TC_10 | Motor | SC_06 | Unnamed PA Value - New Business (New Car) | Must be multiple of 10000 (Premium will be charged at 5 Rs for per person per 10000 SI) Maximum up to 2lacs. * Seating capacity | It is being calculated in multiples of 10000 | Info | [tf-api FG] Unnamed PA SI (multiples of 10000, cap 2L x seating): frontend calculation rule; unnamedPaSumInsured is ICICI-only, FG uses a fixed PACoverForUnnamedPassengers value. | 10 | N/A | N/A
11 | TC_11 | Motor | SC_06 | Unnamed PA Value - Comprehensive | Must be multiple of 10000 (Premium will be charged at 5 Rs for per person per 10000 SI) Maximum up to 2lacs. * Seating capacity | It is being calculated in multiples of 10000 | Info | [tf-api FG] Unnamed PA SI (multiples of 10000, cap 2L x seating): frontend calculation rule; unnamedPaSumInsured is ICICI-only, FG uses a fixed PACoverForUnnamedPassengers value. | 11 | N/A | N/A
12 | TC_12 | Motor | SC_06 | Unnamed PA Value - Third Party | Must be multiple of 10000 (Premium will be charged at 5 Rs for per person per 10000 SI) Maximum up to 2lacs. * Seating capacity | It is being calculated in multiples of 10000 | Info | [tf-api FG] Unnamed PA SI (multiples of 10000, cap 2L x seating): frontend calculation rule; unnamedPaSumInsured is ICICI-only, FG uses a fixed PACoverForUnnamedPassengers value. | 12 | N/A | N/A
13 | TC_13 | Motor | SC_07 | Current NCB - Standalone OD + Next slab of NCB | 1. NCB discount is calculated with Net Basic OD (Premium after OD discount + Premium of Additional Covers * NCB%) | 1. NCB discount is calculated with Net Basic OD (Premium after OD discount + Premium of Additional Covers * NCB%) | Pass (bind pending FG) | [tf-api FG] NCB on Standalone OD: live quote with THIS vehicle — Hyundai Xcent CRDi, expiring NCB 25% -> applicable 35% (next slab, per GCI mapping), SAOD gross ₹2,716 (IDV ₹1,76,092). Journey proven 29-Jul (policy 132/18/11/0827/MOD/2410003314). Fresh binding is currently blocked FG-side (rollover CreateProposal returns 'Vehicle Age is not Configured for this Rule' — GCI's rollover rule deployment in progress, confirmed by GCI mail). | 13 | WB25G7622 | Pending (FG rule fix)
14 | TC_14 | Motor | SC_08 | PUC - Standalone OD | In case of Rollover case PUC is mandatory. Two fields should be added as PUC No, and PUC Expiry Date | If we have selected Valid PUC flag "YES" then following field should be Mandatory. 1. PUC No 2. PUC Expiry Date | Info | [tf-api FG] PUC mandatory on rollover: portal/frontend validation (FG CRT carries Vehicle.ValidPUC flag only). SAOD context quote verified with Hyundai Grand i10 — gross ₹3,284. | 14 | KA02MP1782 | N/A
15 | TC_15 | Motor | SC_09 | Break In - Standalone OD | Break in issuance in not allowed for Aggregators/Brokers. In case allowed, Inspection report to be uploaded by Panel inspection Agency (Live Check and Wimmi Isure) | If recommended by Pre inspection Agency go Ahed, If "Not Recommended" by Pre inspection agency policy not move to issuance. | Pass | [tf-api FG] Break-in Standalone OD: Toyota Innova Crysta with previous policy expired 2023-12-11 — quotes ₹6,202 (risk start today); proposal is gated by 422 INSPECTION_REQUIRED until an inspection report no. is entered (review-page inspection card). Aggregator break-ins not processed on portal. | 15 | MH15GW0234 | N/A
16 | TC_16 | Motor | SC_09 | Break In - Standalone OD - Comprehensive | Break in issuance in not allowed for Aggregators/Brokers. In case allowed, Inspection report to be uploaded by Panel inspection Agency (Live Check and Wimmi Isure) | If recommended by Pre inspection Agency go Ahed, If "Not Recommended" by Pre inspection agency policy not move to issuance. | Pass (bind pending FG) | [tf-api FG] Break-in Comprehensive: Maruti Tour S (policy expired 2025-09-09) quotes ₹10,224 (IDV ₹2,25,050); with inspection ref the proposal proceeds (chain live-proven 14-Jul, ClientID 80042369). Fresh binding is currently blocked FG-side (rollover CreateProposal returns 'Vehicle Age is not Configured for this Rule' — GCI's rollover rule deployment in progress, confirmed by GCI mail). | 16 | TS07UH8906 | Pending (FG rule fix)
17 | TC_17 | Motor | SC_09 | Break In - Third Party Policy | Inspection wavier for Third Party Policy | Policy period (Risk Start Date) should be taken after T+2 days ( i.e. 1. Payment collected date is 09/05/2024 then Risk start date should be 12/05/2024. 2. Issuance time should be pass at the time of policy issuance. Payment collected date is 09/05/2024 04:00:00 then Risk start date should be 11/05/2024 04:01:00.) | Info | [tf-api FG] Break-in Third Party: inspection WAIVER (no OD exposure) — inspectionRequired() returns false for TP; FG applies the T+2 risk-start rule. (TP itself is UW-blocked for this channel.) | 17 | N/A | N/A
18 | TC_18 | Motor | SC_09 | Break In - Standalone OD | In case Break in is > 90 days, current NCB is not allowed | NCB is not offer to this scenarios.(If recommended by Pre inspection Agency go Ahed, If "Not Recommended" by Pre inspection agency policy not move to issuance. ) (Policy period (Risk Start Date) should be taken after T+2 days ( i.e. 1. Payment collected date is 21/07/2023 then Risk start date should be 24/07/2023. 2. Issuance time should be pass at the time of policy issuance. Payment collected date is 21/07/2023 04:30:00 then Risk start date should be 23/07/2023 04:31:00.) | Info | [tf-api FG] Break-in >90 days: NCB not allowed — mapper zeroes applicable NCB when claim/break-in; portal does not process aggregator break-ins (Standalone OD). | 18 | N/A | N/A
19 | TC_19 | Motor | SC_09 | Break In - Comprehensive | In case Break in is > 90 days, current NCB is not allowed | NCB is not offer to this scenarios.(If recommended by Pre inspection Agency go Ahed, If "Not Recommended" by Pre inspection agency policy not move to issuance. ) (Policy period (Risk Start Date) should be taken after T+2 days ( i.e. 1. Payment collected date is 21/07/2023 then Risk start date should be 24/07/2023. 2. Issuance time should be pass at the time of policy issuance. Payment collected date is 21/07/2023 04:30:00 then Risk start date should be 23/07/2023 04:31:00.) | Info | [tf-api FG] Break-in >90 days (Comprehensive): as TC_18 — NCB zeroed; inspection gate enforced by API. | 19 | N/A | N/A
20 | TC_20 | Motor | SC_09 | Owner change - Standalone OD | Transfer of Ownership / Owner change | In Transfer of Ownership case NCB should be ZERO and system allowed to proceed policy with ZERO NCB. | Info | [tf-api FG] Owner change / transfer of ownership: NCB must be zero — portal zeroes NCB; API then issues with NCB 0 (see TC_21 for the zero-NCB issuance path). | 20 | N/A | N/A
21 | TC_21 | Motor | SC_10 | Claim in PYP - Comprehensive | If there is an existing claim, NCB should not be allowed | In case Claim in Previous policy, NCB should be ZERO and system allowed to proceed policy with ZERO NCB. | Pass (bind pending FG) | [tf-api FG] Claim in previous policy: Toyota Fortuner with claim=Y — mapper zeroes applicable NCB (AdditionalBenefit.NCB=0, ClaimInExpiringPolicy=Y); quote ₹65,724 (IDV ₹13,61,850). Zero-NCB issuance proven 29-Jul (policy 132/02/11/0827/MTP/2410003315). Fresh binding is currently blocked FG-side (rollover CreateProposal returns 'Vehicle Age is not Configured for this Rule' — GCI's rollover rule deployment in progress, confirmed by GCI mail). | 21 | RJ01UB1881 | Pending (FG rule fix)
22 | TC_22 | Motor | SC_11 | Vehicle age Above 15 Year's - Comprehensive | If vehicle age>15 years , should not be allowed to show quotes. I.e. Quotes should be visible from T+2 date or next month. | If vehicle age>15 years ,should not be allowed to show quotes. I.e. Quotes should be visible from T+1 date or next month. | Info | [tf-api FG] FG quote API returned a price for a 17-yr-old car (PROPOSAL); the >15yr restriction is enforced on the portal frontend (quotes hidden). | 22 | MH43AB424 | N/A
23 | TC_23 | Motor | SC_13 | Standalone Add-on covers - Comprehensive | NCB protection and Inconvenience allowance is not allowed without Zero Dep | NCB protection and inconvenience allowance should be not standalone addon (without Zero Dep) | Pass | [tf-api FG] NCB Protection / Inconvenience Allowance are not standalone: enforced via FG add-on combo codes (requiresZeroDep) — not priced without Zero-Dep. | 23 | N/A | N/A
24 | TC_24 | Motor | SC_14 | Discount - New Business (New Car) | Check correct discount passing or not | CO-1+3-Verify OD TP Premium | Pass | [tf-api FG] New Business CO 1+3: OD ₹9,965 + TP ₹6,521 (OD special discount 70%, echoed at CRT), gross ₹19,453. ISSUED. | 24 | TN68AJ6125 | 132/14/11/0729/MTP/2410003316
25 | TC_25 | Motor | SC_15 | Discount - Comprehensive | Check correct discount passing or not | CO-1+1 - Verify TP Premium | Pass | [tf-api FG] Rollover CO 1+1: OD ₹15,801 + TP ₹3,416 (OD special discount 0% echoed at CRT), gross ₹18,947. ISSUED. | 25 | MH03DK2902 | 132/02/11/0827/MTP/2410003317
26 | TC_26 | Motor | SC_16 | Decline Make Model - NSTP Flow - New Business (New Car) | Decline Make Model | System should not be allowed to issued policy with Decline Make Model. | Pass | [tf-api FG] Declined make/model (MMV code MA0197, Swift VXI ABS): FG refuses at proposal ("Vehicle Is Decline") — policy cannot be issued with a declined make/model. Quote-stage declines also observed for other declined models ("Referral due to: Declined Vehicle"). | 26 | N/A | N/A
27 | TC_27 | Motor | SC_17 | Decline RTO code - Haryana - New Business (New Car) | Decline RTO code - Haryana | System should not be allowed to issued policy with Decline RTO code. HR-38 | Pass | [tf-api FG] Declined RTO HR-38: quote refused — "Referral due to: Declined Vehicle". | 27 | N/A | N/A
28 | TC_28 | Motor | SC_18 | Blacklisted Vehicle - Comprehensive | Blacklisted Vehicle | MH02EP6349, MH02EE7034, MH14DX6896, GJ05RB3983 | Info | [tf-api FG] Blacklisted plate MH02EP6349 was NOT blocked in UAT — policy issued (132/02/11/0827/MTP/2410003318); GCI to confirm blacklist runs at production/issuance stage. Portal shows the block message client-side. | 28 | MH02EP6349 | 132/02/11/0827/MTP/2410003318
29 | TC_29 | Motor | SC_19 | Add-On Age limit - Comprehensive | Add-On Age limit - Up to 7 Years | Zero Dep + RSA + Personal Belonging + Key Loss + Consumable + Engine Protector up to Age 7 years. (ZDCNE) | Pass | [tf-api FG] Add-on age limit: Hyundai i20 (reg 2016, ~10 yrs) quotes ₹5,929, but Zero-Dep combo covers (STZDP/ZDCNE <7 yrs per Add-On master) are age-gated and disabled for this vehicle in the portal. | 29 | TS07EZ0804 | N/A
30 | TC_30 | Motor | SC_20 | Advance Inception - Standalone OD | Advance policy inception date cannot be more than 45 days. | System should be allowed to issued policy Advance inception day's 45. | Pass | [tf-api FG] Advance inception is capped at 45 days: a rollover whose policy would start +61 days is refused with a clear message ("policy can start at most 45 days in advance; come back within 45 days of expiry") BEFORE hitting FG. Within-window starts (+8d) issue normally (see TC_03/25). Root cause of the earlier "Reinsurance" errors was exactly this — starts beyond the treaty window. | 30 | DL10CN1591 | N/A
31 | TC_31 | Motor | SC_21 | Duplicate Registration - Standalone OD | Duplicate Registration number should not allow to create policy | MH01UH5433, MH01UH8756 | Info | [tf-api FG] Duplicate registration NOT blocked in UAT — issued (132/18/11/0827/MOD/2410003319); duplicate check is production/issuance-stage per GCI. Portal enforces the pop-up client-side. (Standalone OD) | 31 | MH01UH5433 | 132/18/11/0827/MOD/2410003319
32 | TC_32 | Motor | SC_22 | Duplicate Registration - Comprehensive | Duplicate Registration number should not allow to create policy | MH01UH5433, MH01UH8756 | Info | [tf-api FG] Duplicate registration NOT blocked in UAT — issued (132/02/11/0827/MTP/2410003320). (Comprehensive) | 32 | MH01UH5433 | 132/02/11/0827/MTP/2410003320
33 | TC_33 | Motor | SC_23 | UW Validation -Excluded Covers - (New Car) - New Business | Anti theft | Anti theft cover is not offer to Web Aggregator | Pass | [tf-api FG] Anti-theft cover is not exposed by the tf-api FG provider (absent from the canonical add-on set; never sent to FG). Not offered to Web Aggregator, as expected. | 33 | N/A | N/A
34 | TC_34 | Motor | SC_24 | UW Validation -Excluded Covers New Business (New Car) | Geographical area | Geographical cover is not offer to Web aggregator | Pass | [tf-api FG] Geographical area cover is not exposed by the tf-api FG provider (absent from the canonical add-on set; never sent to FG). Not offered to Web Aggregator, as expected. | 34 | N/A | N/A
35 | TC_35 | Motor | SC_25 | UW Validation -Excluded Covers - New Business (New Car) | AAI - (Auto Mobile Association Membership) | AAI cover is not offer to Web aggregator | Pass | [tf-api FG] AAI membership cover is not exposed by the tf-api FG provider (absent from the canonical add-on set; never sent to FG). Not offered to Web Aggregator, as expected. | 35 | N/A | N/A
36 | TC_36 | Motor | SC_26 | UW Validation -Excluded Covers - New Business (New Car) | Restricted TPPD | Restricted TPPD cover is not offer to Web aggregator | Pass | [tf-api FG] Restricted TPPD cover is not exposed by the tf-api FG provider (absent from the canonical add-on set; never sent to FG). Not offered to Web Aggregator, as expected. | 36 | N/A | N/A
37 | TC_37 | Motor | SC_27 | CKYC Verification - HB-Individual | CKYC Verification fail & document uploading | CKYC Verification failed if Wrong PAN or DOB details updated. | Pass | [tf-api FG] CKYC with wrong PAN (ABCDE1234F) correctly FAILS (no CKYC record) — portal routes to OVD document upload. Valid PAN DHQPG4064J -> CKYC 40053862382888 (Meenu Gupta). | 37 | N/A | N/A

## Screenshots
tf-api FG provider — customer journey, screen by screen (captured on the live portal http://localhost:8080, backend tf-api + live FG UAT). Each screen lists the test cases it evidences.
Screen 1 — Home / product selection
Applies to: All journeys (TC_01–TC_05, TC_24, TC_25)
Screen 2 — Login (registered mobile)
Applies to: All journeys
Screen 3 — Car number entry (DL10CN1591)
Applies to: TC_03, TC_07, TC_21, TC_25, TC_30
Screen 4 — RC details auto-fetched (Honda City, prev insurer + expiry)
Applies to: TC_03, TC_07, TC_25, TC_30
Screen 5 — Plans (Comprehensive): live compare, IDV control, NCB, claim toggle
Applies to: TC_03, TC_07 (IDV min/max band), TC_25
Screen 6 — Plans (Third-Party): FG not offered (GCI UW block) — ICICI only
Applies to: TC_04
Screen 7 — Plans (Standalone OD): previous TP policy details required (insurer/number/dates)
Applies to: TC_02, TC_13, TC_14
Screen 8 — Plans with NCB 25% selected (premium reprices)
Applies to: TC_13, TC_21 (claim ⇒ NCB zeroed)
Screen 9 — FG 45-day advance-inception message (policy would start 2026-10-09; renewal window opens within 45 days of expiry)
Applies to: TC_30 (also the root cause behind the earlier 'Reinsurance' errors)
Screen 10 — New car (no reg yet): manual make/model + RTO + purchase date
Applies to: TC_01, TC_05, TC_24 (F13 new-business journey)
Screen 11 — Proposer details (name/DOB/gender/address, engine & chassis, nominee/CPA fields)
Applies to: TC_01–TC_03, TC_06 (CPA/nominee capture)
Screen 12 — KYC verification FAILS for wrong PAN (ABCDE1234F) → Aadhaar / OVD document-upload fallback offered
Applies to: TC_37
Note: FG-priced screens (FG premium card, FG add-on panel, Review with FG premium breakdown, payment hand-off) are captured API-side in the Testcases sheet (11 real policy numbers); FG UAT's quote service was intermittently down during this capture window — those three UI screens can be re-captured on recovery.

## Partner Frontend validation (hidden)
Note : These are the Buisness core validation. TCS service will throw these error message that need to be shown/ display on portal frontend.
SrNo | Testcase | Remark | Fronened validation
1 | Vehicle age validation | If vehicle age>15 years ,Sytem should not show quotes. I.e Quotes should be visible from T+2 date or next month. | Screenshot of Quote page is required.
2 | Decline make model | System should not be allowed to issued policy with Decline make model | Screenshot of error message to be shown before payment.
3 | Decline RTO code - Hariyana | System should not be allowed to issued policy with Decline RTO code. HR-38 | Screenshot of error message to be shown before payment.
4 | Blacklisted Vechile | Pop up message displayed, Registration No: MH-05-CV-3388 is blocked in System. MH02EP5784, MH05CV3388 ,MH27BZ8880 | Screenshot of error message to be shown before payment.
5 | Advance Inception | System should be allowed to issued policy Advance inception day's 45 | Screenshot of Quote page is required.
6 | Duplicate Resgistration | Pop up message should display , Same Registration Number exists in Active. | Screenshot of error message to be shown before payment.